## Band Shell
Town of Barnstable: Priority for ADA Transition Plan - Secondary Assets
**IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Barnstable
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Band Shell | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) K. Surface is not stable, firm, and slip-resistant | Walkway From Base of Ramp to Front of Band Shell | Ext |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). Repair surface. (Cost based on a 4' wide min. x 30' long stone dust path from the base of the ramp running along the Band Shell structure to the northwest corner at by the front of the stage.) | 1 | 960
2 | Band Shell | C. Ramps | H. Handrails do not extend 12" past top & bottom J. Handrails have non-compliant cross section L. Handrails not continuous where required | Ramp From Ocean Street Parking Lot to Village Green (Right Side) | Ext |  | Priority 3 | Additional Access | Alter handrails to extend horizontally above the landing for 12" min. beyond the bottom of the ramp run. Provide handrails with 1-1/4"to 1-1/2" circular cross section. Provide continuous handrails for the length of the ramp run.(Cost based on 4 30' sections of metal handrail (upper and lower) with a compliant cross section for right-side ramp.) | 1 | 8880
3 | Band Shell | C. Ramps | R. Edge protection < 4" high | Ramp From Ocean Street Parking Lot to Village Green (Right Side) | Ext |  | Priority 3 | Additional Access | Provide edge protection that prevents the passage of a 4" diameter sphere, where any portion of the sphere is within 4" of the finished floor or ground surface. (Cost based on 30' of edge protection along the right-most side of the ramp to the Village Green.) | 1 | 2520
4 | Band Shell | Bench |  | Ext. | Ext |  | Priority 4 | Enhanced Usability | Recommend providing at least one bench on existing walkway facing the performance area at the Band Shell. Recommend providing a 3'x4' min. firm, stable and slip-resistant surface at one end of the bench facing the Band Shell so an individual using a wheeled mobility or similar device could sit at one end of the bench with his or her shoulders aligned with someone seated on the bench. | 1 | 0
5 | Band Shell | Exterior Stairs |  | Front of Band Shell | Ext |  | Priority 4 | Enhanced Usability | Recommend providing railings on one side of Band Shell steps to facilitate access between the Band Shell performance area and the Village Green. | 1 | 0
6 | Band Shell | Exterior Railing |  | Walkway From Ocean Street Lot to Band Shell Performance Area | Ext |  | Priority 4 | Enhanced Usability | Recommend, on left side of walkway to the Band Shell stage that is not a ramp due to the less than 1:20 (5.00%) running slope, providing handrails with 1-1/4" to 1-1/2" circular cross section. | 1 | 0

## Creative Arts 2
Town of Barnstable: Priority for ADA Transition Plan - Secondary Assets
**IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Barnstable
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Creative Arts 2 | A. Exterior Access Route | N. Accessible route not provided | Entrance to Art Studio | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided. (Cost estimate of 4' wide and 6' long concrete path.) | 1 | 384
2 | Creative Arts 2 | A. Exterior Access Route | N. Accessible route not provided | Information Sign Near Parking Lot | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to and around art exhibits. | 1 | 576
3 | Creative Arts 2 | A. Exterior Access Route | N. Accessible route not provided | Information Sign Near Creative Arts | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the sign. (Cost estimate of 4' wide and 15' long stone dust path.) | 1 | 480
4 | Creative Arts 2 | A. Exterior Access Route | N. Accessible route not provided | Exterior Art Installations by Creative Arts | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to and around art exhibit. (Cost estimate of 4' min. wide and 90' long stone dust path.) | 1 | 2880
5 | Creative Arts 2 | E. Exterior Ramp | J. Level changes > 1/4" | Main Entrance/Egress to Creative Arts | Ext. |  | Priority 1 | Program Access | Alter change in level to be 1/4" high max. | 1 | 256
6 | Creative Arts 2 | G. Entrance | G. Maneuvering clearance is not provided | Main Entrance/ Egress at Creative Arts | Ext. |  | Priority 1 | Program Access | Provide an automatic door opener. (18" min. pull side maneuvering clearance is required on the pull-side of the door.) | 1 | 3060
7 | Creative Arts 2 | A. Means of Egress | B. Tactile exit sign not provided | Entrance/Egress at Art Studio | Ext. |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. If the exit sign is replaced with an illuminated exit sign, provide an illuminated International Symbol of Accessibility (ISA). | 1 | 232
8 | Creative Arts 2 | A. Means of Egress | B. Tactile exit sign not provided | Main Entrance/ Egress at Creative Arts | 1 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 232
9 | Creative Arts 2 | A. Means of Egress | B. Tactile exit sign not provided C. Directional sign to accessible emergency exit not provided | Creative Arts 2 Egress Door west Side | 1 |  | Priority 1 | Safety | Provide a directional sign indicating the location of the nearest accessible emergency exit. Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 464
10 | Creative Arts 2 | A. Means of Egress | B. Tactile exit sign not provided C. Directional sign to accessible emergency exit not provided | Creative Arts 2 Egress Door north Side | 1 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide a directional sign indicating the location of the nearest accessible emergency exit. | 1 | 464
11 | Creative Arts 2 | B. Interior Access Route | B. Obstructed by protruding objects | Creative Arts Room 3 | 1 |  | Priority 3 | Additional Access | Provide a cane-detectable barrier at the wall cabinet. | 1 | 306
12 | Creative Arts 2 | C. Doors, Doorways, & Gates | A. Clear width at door < 32" | Creative Arts 2 Emergency Exit on North Side | 1 |  | Priority 3 | Additional Access | Widen the door so that there is 32" min. clear width. | 1 | 2232
13 | Creative Arts 2 | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Creative Arts 2 Single-User Toilet Room | 1 |  | Priority 3 | Additional Access | Provide an automatic door opener. (18" min. pull side maneuvering clearance is required on the pull-side of the door.) | 1 | 3060
14 | Creative Arts 2 | K. Operable Parts | C. Reach < 15" or > 48"(forward/side approach) | Near Entrance to the Art Studio | Ext. |  | Priority 3 | Additional Access | Relocate chains so that they are between 15"- 48" above the finished floor. | 1 | 0
15 | Creative Arts 2 | B. Lavatory | B. Toe or knee clearances not provided | Creative Arts 2 Single-User Toilet Room | 1 |  | Priority 1 | Program Access | Provide at least one lavatory with knee and toe clearance positioned for a forward approach. | 1 | 1686
16 | Creative Arts 2 | C. Single-User Toilet | B. Flush control not on open side | Creative Arts 2 Single-User Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate the flush control to the open side. | 1 | 374
17 | Creative Arts 2 | C. Single-User Toilet | O. Hook located > 48" high | Creative Arts 2 Single-User Toilet Room | 1 |  | Priority 3 | Additional Access | Locate hook no higher than 48" above the finished floor. | 1 | 150

## Joshua's Pond and Bathhouse
Town of Barnstable: Priority for ADA Transition Plan - Secondary Assets
**IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Barnstable
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Joshua's Pond and Bath House | A. Exterior Access Route | H. Running slope > 1:20 (5%) K. Surface is not stable, firm, and slip-resistant N. Accessible route not provided | Pond Access Route | Ext. |  | Priority 1 | Program Access | Providing an accessible route might be technically infeasible. | 1 | 0
2 | Joshua's Pond and Bath House | E. Off-Street Parking Lot or Garage | P. Sign bottom < 60" above finished grade | Accessible Parking Spots | Ext. |  | Priority 1 | Program Access | Locate sign with the bottom of the sign 60" above the ground. | 1 | 0
3 | Joshua's Pond and Bath House | D. Stairways | C. Handrails do not extend 12" from stairs H. Treads < 11" deep N. Accessible route not provided P. Tread widths and/or riser heights are not uniform | Pond Access Route | Ext. |  | Priority 1 | Program Access | Providing an accessible route might be technically infeasible. | 1 | 0
4 | Joshua's Pond and Bath House | E. Signage | B. Raised characters not provided D. Braille not provided G. Sign not located on the latch side of the door | Route From Parking to Men's Toilet Room | Ext. |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille. Locate sign at permanent rooms alongside the door on the latch side. | 1 | 232
5 | Joshua's Pond and Bath House | E. Signage | B. Raised characters not provided D. Braille not provided G. Sign not located on the latch side of the door | Route From Parking to Women's Toilet Room | Ext. |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille. Locate sign at permanent rooms alongside the door on the latch side. | 1 | 232
6 | Joshua's Pond and Bath House | F. Service Counter | B. Counter > 36" high | Parking Hut | Ext. |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the ground. | 1 | 880
7 | Joshua's Pond and Bath House | J. Picnic Tables | H. Picnic table not on an accessible route | Field With Picnic Table | Ext. |  | Priority 1 | Program Access | Ensure that the picnic table is connected to an accessible route. (Cost of 4' wide by 12' long concrete path.) | 1 | 600
8 | Joshua's Pond and Bath House | B. Lavatory | E. Exposed plumbing underneath | Men's Toilet Room | 1 |  | Priority 1 | Safety | Insulate or otherwise configure pipes to prevent contact for at least one lavatory. | 1 | 92
9 | Joshua's Pond and Bath House | B. Lavatory | E. Exposed plumbing underneath | Women's Toilet Room | 1 |  | Priority 1 | Safety | Insulate or otherwise configure pipes to prevent contact for at least one lavatory. | 1 | 92
9 | Joshua's Pond and Bath House | B. Lavatory | E. Dispenser acts as a protruding object | Women's Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate paper towel dispenser out of circulation path. | 1 | 256
10 | Joshua's Pond and Bath House | D. Toilet Compartment | D. Door with malfunctioning self-closing hinge | Men's Toilet Room | 1 |  | Priority 3 | Additional Access | Repair hinge. | 1 | 0
11 | Joshua's Pond and Bath House | D. Toilet Compartment | D. Door with malfunctioning self-closing hinge | Women's Toilet Room | 1 |  | Priority 3 | Additional Access | Repair hinge. | 1 | 0
12 | Joshua's Pond and Bath House | F. Dispensers | A. Controls > 42" (MAAB) E. Dispenser acts as a protruding object | Men's Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate so the operable part is 42" max. above the finished floor. Relocate hand sanitizer out of circulation path. | 1 | 0
13 | Joshua's Pond and Bath House | F. Dispensers | A. Controls > 42" (MAAB) E. Dispenser acts as a protruding object | Women's Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate hand sanitizer so the operable part is 42" maximum above the finished floor. Relocate hand sanitizer out of circulation path. | 1 | 0
14 | Joshua's Pond and Bath House | H. Outdoor Rinsing Showers | D. 2 fixed showerheads not provided | Outdoor Shower | Ext. |  | Priority 1 | Program Access | Provide two showerheads located 48" and 72" min. above the ground. | 1 | 2719

## Lombard Field
Town of Barnstable: Priority for ADA Transition Plan - Secondary Assets
**IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Barnstable
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Lombard Field | A. Exterior Access Route | E. Route obstructed by protruding objects | Dugouts | Ext. |  | Priority 3 | Additional Access | Provide a cane-detectable barrier at the electric boxes located at both dugouts. | 2 | 612
2 | Lombard Field | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Route From Parking Lot to Bleachers, Dugout, and Score Box | Ext. |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). (Cost for 4' by 10' of asphalt to reduce cross slope.) | 1 | 400
3 | Lombard Field | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Route From Parking Lot to Bleachers and Dugout | Ext. |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). (Cost for 4' by 10' of asphalt to reduce cross slope.) | 1 | 600
4 | Lombard Field | A. Exterior Access Route | H. Running slope > 1:20 (5%) | Route From Parking Lot to Bleachers, Dugout, and Score Box | Ext. |  | Priority 3 | Additional Access | Reduce running slope to be no steeper than 1:20 (5%). (Cost for 4' by 15' of asphalt to reduce running slope.) | 1 | 600
5 | Lombard Field | C. Field | A. Accessible spaces are not provided at team seating | Dugouts | Ext. |  | Priority 1 | Program Access | Provide a 36" x 48" clear floor space at both team seating dugouts. | 2 | 0
6 | Lombard Field | C. Field | B. Accessible spaces not provided at sidelines seating | Bleachers at Right Side of Home Plate | Ext. |  | Priority 1 | Program Access | Provide a 36" x 48" firm and stable clear floor space at sidelines seating with a max. slope of 2.00% in all directions. (Cost for 3' X 4' of asphalt.) | 1 | 120
7 | Lombard Field | G. Bleachers | D. Seating spaces < 36" x 48" (single space) | Bleachers at Left Side of Home Plate | Ext. |  | Priority 3 | Additional Access | Provide a 36" x 48" firm and stable clear floor space at sidelines seating with a max. slope of 2.00% in all directions. (Cost for 3' X 4' of asphalt.) | 1 | 120

## Meetinghouse Farm Barn
Town of Barnstable: Priority for ADA Transition Plan - Secondary Assets
**IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Barnstable
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Meetinghouse Farm Barn | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) H. Running slope > 1:20 (5%) K. Surface is not stable, firm, and slip-resistant N. Accessible route not provided | Path Through the Rhododendron Forest | Ext. |  | Priority 1 | Program Access | Reduce cross slope to be no steeper than 1:50 (2.00%). Reduce running slope to be no steeper than 1:20 (5%). Repair surface. Ensure an accessible route is provided. (Cost to provide an accessible route through the Rhododendron Forest not provided.) | 1 | 0
2 | Meetinghouse Farm Barn | A. Exterior Access Route | N. Accessible route not provided | Route From Barn to Start of Rhododendron Forest Path | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided. Cost based on a 4' wide min. x 45' long stone dust path from the north side of the building to the entry point of the Rhododendron Forest path by the bench and sign. | 1 | 2880
3 | Meetinghouse Farm Barn | A. Exterior Access Route | N. Accessible route not provided | Stairs to Second Floor - North Side | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the landing for the stairs to the second floor entry door. Ensure route has a 1:20 (5%) max. running and 1:50 (2%) max. cross slope. (Cost based on a 4' wide min. x 45' long stone dust path from the parking area to the stair landing.) | 1 | 2880
4 | Meetinghouse Farm Barn | C. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated accessible parking spaces C. Total # of designated van accessible spaces G. Access aisle not provided N. Sign not provided | Parking at Barn | Ext. |  | Priority 1 | Program Access | Provide a van accessible parking space and a marked access aisle each at least 96" wide. Provide a sign with the International Symbol of Accessibility (ISA) and the words "Van Accessible" with the bottom of the sign 60" min. above the ground and the top 96" max. above the ground. (See the narrative report for an example of how to designate parking in an unpaved area.) | 1 | 1850
5 | Meetinghouse Farm Barn | G. Entrance | B. Entrance not on an accessible route | Route to Stairs to Second Floor - North Side | Ext. |  | Priority 1 | Program Access | Provide a compliant exterior ramp with handrails, edge protection and landings running along the north side of the structure and connecting with the second floor entry door. See Figure 1 in the narrative report. (Cost based on a 30' straight pressure-treat wood ramp.) | 1 | 7843
6 | Meetinghouse Farm Barn | H. Emergency Exit | P. Threshold > 1/2" high | Second Floor Egress Door Threshold | 2 |  | Priority 3 | Additional Access | Alter the threshold to be 1/2" high max. | 1 | 150
7 | Meetinghouse Farm Barn | E. Stairways | B. Handrail height < 34" or > 38" C. Handrail not provided on both sides E. Handrails have non-compliant cross section | Stairs to Second Floor | Ext. |  | Priority 3 | Additional Access | Alter so the handrails are 34"- 38" high above the floor. Provide handrail on both sides with 1 1/4" - 2" circular cross section. (Cost based on two 10' long wooden handrails mounted between 34" and 38" high.) | 1 | 880
8 | Meetinghouse Farm Barn | T. Exterior Benches | A. No accessible route to one bench in area | Lawn Behind Barn | Ext. |  | Priority 1 | Program Access | Provide an accessible route to at least one bench in each area where benches are provided. (Cost included in the cost for the 45' stone dust path to the Rhododendron Forest entry point.) | 1 | 0

## Office, Greenhouse and Garage
Town of Barnstable: Priority for ADA Transition Plan - Secondary Assets
**IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Barnstable
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Office, Greenhouse and Garage | C. Off-Street Parking Lot or Garage | A. Total # of parking C. Total # of designated van accessible spaces O. Sign does not have the designation "Van Accessible" Q. Sign top > 96" above finished grade | Parking Lot | Ext. |  | Priority 1 | Program Access | Add the designation "Van Accessible" to the sign located at the van accessible space. Locate sign with the top of the sign 96" above the ground. | 1 | 500
2 | Office, Greenhouse and Garage | G. Entrance | B. Entrance not on an accessible route | Office Entrance | Ext. |  | Priority 1 | Program Access | Provide a ramp accessible route to the entrance. (Cost of 6' foot straight ramp.) | 1 | 1600
3 | Office, Greenhouse and Garage | H. Emergency Exit | B. Tactile sign not provided at exit C. Directional sign to accessible emergency exit not provided | Egress - West Side | 1 |  | Priority 1 | Program Access | Provide tactile exit signs with raised characters and braille at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. Provide a directional sign indicating the location of the nearest accessible entrance/emergency exit. | 2 | 464
4 | Office, Greenhouse and Garage | C. Doors, Doorways, & Gates | A. Clear width at door < 32" | Meeting Room | 1 |  | Priority 3 | Additional Access | Widen the door so that there is 32" min. clear width. | 1 | 3366
5 | Office, Greenhouse and Garage | C. Doors, Doorways, & Gates | A. Clear width at door < 32" C. Maneuvering clearance(s) not provided | Main Office | 1 |  | Priority 3 | Additional Access | Widen the door so that there is 32" min. clear width. Move the piano to provide 18" maneuvering clearance at the hardware side of the door. | 1 | 3366
6 | Office, Greenhouse and Garage | C. Doors, Doorways, & Gates | A. Clear width at door < 32" C. Maneuvering clearance(s) not provided L. Hardware not operable with a closed fist | Main Entrance | 1 |  | Priority 1 | Program Access | Widen the door so that there is 32" min. clear width. Provide 18" maneuvering clearance at the hardware side of the door. Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. | 1 | 3850
7 | Office, Greenhouse and Garage | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Toilet Room | 1 |  | Priority 3 | Additional Access | Provide maneuvering clearance at door. (Cost provided in ID #9.) | 1 | 0
8 | Office, Greenhouse and Garage | C. Single-User Toilet | E. Grab bar not provided | Toilet Room | 1 |  | Priority 1 | Program Access | Provide one grab bar on the side wall of the toilet and one on the rear wall. (Cost provided in ID #9.) | 1 | 0
9 | Office, Greenhouse and Garage | C. Single-User Toilet | L. Clearance at toilet < 72" clear depth | Toilet Room | 1 |  | Priority 3 | Additional Access | Renovate the toilet room to ensure that there is 72" deep min. clear floor space at the toilet. | 1 | 24604

## Sandy Neck Beach Gatehouse
Town of Barnstable: Priority for ADA Transition Plan - Secondary Assets
**IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Barnstable
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Sandy Neck Beach Gatehouse | A. Exterior Access Route | K. Surface is not stable, firm, and slip-resistant | Path to Gate House From Parking Lot | Ext. |  | Priority 3 | Additional Access | Repair surface. (Cost of 4' wide by 12' long concrete path from access aisle to street crossing.) | 1 | 768
2 | Sandy Neck Beach Gatehouse | C. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated accessible parking spaces C. Total # of designated van accessible spaces R. Surface not stable, firm, and slip-resistant | Parking Lot | Ext. |  | Priority 1 | Program Access | Provide a compliant van accessible parking space with a marked access aisle. Include a designation sign with the International Symbol of Accessibility (ISA) and the designation "Van Accessible" (Cost for a van accessible space with a concrete surface for the space and access aisle.) | 1 | 6458
3 | Sandy Neck Beach Gatehouse | E. Exterior Ramp | J. Handrails < 1 1/2" to adjacent surface Q. Edge protection < 4" high | Ramp to Bathhouse Entrance | Ext. |  | Priority 3 | Additional Access | Alter the handrails so they are mounted 1-1/2" min. from adjacent surface. Provide edge protection that prevents the passage of a 4" diameter sphere, where any portion of the sphere is within 4" of the finished floor or ground surface. | 2 | 2520
4 | Sandy Neck Beach Gatehouse | C. Doors, Doorways, & Gates | C. Maneuvering clearance(s) not provided | Toilet Room | 1 |  | Priority 3 | Additional Access | Provide an automatic door opener. | 1 | 3060
5 | Sandy Neck Beach Gatehouse | C. Doors, Doorways, & Gates | K. Threshold > 1/2" high | Bathhouse Entrance | Ext. |  | Priority 3 | Additional Access | Alter the threshold to be 1/2" high max. | 1 | 150
6 | Sandy Neck Beach Gatehouse | K. Operable Parts | D. Side reach > 54" | Ramp to Bathhouse Entrance | Ext. |  | Priority 3 | Additional Access | Relocate application box so that controls are between 15" - 48" above the finished floor. | 1 | 0
7 | Sandy Neck Beach Gatehouse | K. Operable Parts | D. Side reach > 54" | Bathhouse Entrance | Ext. |  | Priority 3 | Additional Access | Relocate sign in sheets box so that controls are between 15" - 48" above the finished floor. | 1 | 0
8 | Sandy Neck Beach Gatehouse | B. Lavatory | F. Mirror above lavatory w/reflective surface > 40" | Toilet Room | 1 |  | Priority 3 | Additional Access | Lower mirror so that the bottom surface is at 40" max. above the finished floor. | 1 | 256
9 | Sandy Neck Beach Gatehouse | C. Single-User Toilet | D. Centerline < or > 18" (MAAB) G. Side or rear grab bar < 33" or > 36" high L. Clearance at toilet < 72" clear depth M. Toilet paper dispenser is not compliant | Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate toilet so that the centerline is 18" from the side wall. Mount grab bars 33"- 36" above the floor. Relocate cabinet. Relocate toilet paper so that it is 24" min. high, located under the grab bar, and between 7" and 9" from the front of the toilet. | 1 | 3340

## Sea St. Bath. & Keyes Mem.Beach
Town of Barnstable: Priority for ADA Transition Plan - Secondary Assets
**IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Barnstable
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Sea Street Bathhouse and Keyes Memorial Beach | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Route From Parking Lot to Bathhouse | Ext. |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
2 | Sea Street Bathhouse and Keyes Memorial Beach | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Route to Bathhouse | Ext. |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
3 | Sea Street Bathhouse and Keyes Memorial Beach | A. Exterior Access Route | H. Running slope > 1:20 (5%) | Route From Parking Lot to Bathhouse | Ext. |  | Priority 3 | Additional Access | Reduce running slope to be no steeper than 1:20 (5.00%). | 1 | 0
4 | Sea Street Bathhouse and Keyes Memorial Beach | A. Exterior Access Route | H. Running slope > 1:20 (5%) | Route From Parking Lot to Bathhouse | Ext. |  | Priority 3 | Additional Access | Reduce running slope to be no steeper than 1:20 (5.00%). | 1 | 0
5 | Sea Street Bathhouse and Keyes Memorial Beach | A. Exterior Access Route | H. Running slope > 1:20 (5%) | Route From Parking Lot to Bathhouse | Ext. |  | Priority 3 | Additional Access | Reduce running slope to be no steeper than 1:20 (5.00%). | 1 | 0
6 | Sea Street Bathhouse and Keyes Memorial Beach | A. Exterior Access Route | K. Surface is not stable, firm, and slip-resistant M. Route not maintained in operable working condition | Route to Viewing Area | Ext. |  | Priority 1 | Program Access | Repair surface. Ensure the accessible route is maintained in operable working condition. | 1 | 0
7 | Sea Street Bathhouse and Keyes Memorial Beach | A. Exterior Access Route | M. Route not maintained in operable working condition | Route From Sea Street Extension to Bathhouse | Ext. |  | Priority 1 | Program Access | Ensure the accessible route is maintained in operable working condition. | 1 | 0
8 | Sea Street Bathhouse and Keyes Memorial Beach | A. Exterior Access Route | N. Accessible route not provided | Towards Beach | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the volleyball area. See ID #9. | 1 | 0
9 | Sea Street Bathhouse and Keyes Memorial Beach | C. Beach Access Routes | A. Beach route not provided | Towards Beach | Ext. |  | Priority 1 | Program Access | Provide an accessible route that is firm and stable. Ensure the accessible route extends to the high tide level. Cost for a 5 ft wide by 100 ft. long beach mat. | 1 | 8777
10 | Sea Street Bathhouse and Keyes Memorial Beach | C. Beach Access Routes | C. Surface is not firm and stable | Route From Parking Lot to Beach | Ext. |  | Priority 3 | Additional Access | Ensure surface at the accessible route is firm and stable. | 1 | 0
11 | Sea Street Bathhouse and Keyes Memorial Beach | C. Beach Access Routes | E. Level changes > 1/4" | Route From Parking Lot to Beach | Ext. |  | Priority 3 | Additional Access | Ensure change in level is not greater than 1/4" high max. | 1 | 0
12 | Sea Street Bathhouse and Keyes Memorial Beach | E. Off-Street Parking Lot or Garage | G. Access aisle not provided O. Sign does not have the designation "Van Accessible" | Parking Lot | Ext. |  | Priority 1 | Program Access | Provide three marked access aisles that are at least 96" wide. Add the designation "Van Accessible" to the sign located at the van accessible space. | 1 | 1400
13 | Sea Street Bathhouse and Keyes Memorial Beach | C. Ramps | J. Handrails have non-compliant cross section R. Edge protection < 4" high | Route From Parking Lot to Bathhouse | Ext. |  | Priority 3 | Additional Access | Provide handrails with 1-1/4" to 1-1/2" circular cross section. Ensure handrails return to to the landing surface. Provide edge protection that prevents the passage of a 4" diameter sphere, where any portion of the sphere is within 4" of the finished ground surface. | 1 | 5160
14 | Sea Street Bathhouse and Keyes Memorial Beach | C. Ramps | O. Landing has a slope > 1:50 (2.00%) (MAAB) | Ramp by Parking Lot | Ext. |  | Priority 3 | Additional Access | Alter so that the slope in all directions is no greater than 1:50 (2.00%). | 1 | 0
15 | Sea Street Bathhouse and Keyes Memorial Beach | C. Ramps | R. Edge protection < 4" high | Ramp -Employee's Office Side | Ext. |  | Priority 3 | Additional Access | Provide edge protection that prevents the passage of a 4" diameter sphere, where any portion of the sphere is within 4" of the finished floor or ground surface. | 1 | 2520
16 | Sea Street Bathhouse and Keyes Memorial Beach | C. Ramps | R. Edge protection < 4" high | Ramp -Toilet Rooms Side | Ext. |  | Priority 3 | Additional Access | Provide edge protection that prevents the passage of a 4" diameter sphere, where any portion of the sphere is within 4" of the finished floor or ground surface. | 1 | 2520
17 | Sea Street Bathhouse and Keyes Memorial Beach | E. Signage | B. Raised characters not provided D. Braille not provided G. Sign not located on the latch side of the door | Women's Toilet Room | 1 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille. Locate sign at permanent rooms alongside the door on the latch side. | 1 | 232
18 | Sea Street Bathhouse and Keyes Memorial Beach | F. Service Counter | B. Counter > 36" high | Bathhouse - Sea Street Side | Ext. |  | Priority 3 | Additional Access | Provide a counter that is 36" max. above the ground. | 1 | 880
19 | Sea Street Bathhouse and Keyes Memorial Beach | J. Picnic Tables | G. Toe or knee clearance at table not provided H. Picnic table not on an accessible route | Picnic Area /next to Employee's Side Ramp | Ext. |  | Priority 1 | Program Access | Provide at least one picnic table with top between 28"- 34" above the ground and 27" clear height underneath. Ensure that the dining surface is connected to an accessible route. | 1 | 1400
20 | Sea Street Bathhouse and Keyes Memorial Beach | J. Picnic Tables | G. Toe or knee clearance at table not provided H. Picnic table not on an accessible route | Picnic Area Next to Ramp by Toilet Rooms | Ext. |  | Priority 1 | Program Access | Provide at least one picnic table with top between 28"- 34" above the ground and 27" clear height underneath. Ensure that the dining surface is connected to an accessible route. | 1 | 1400
21 | Sea Street Bathhouse and Keyes Memorial Beach | K. Grills | A. Not on a accessible route | Picnic Area | Ext. |  | Priority 1 | Program Access | Ensure grills are located on an accessible route. | 1 | 0
22 | Sea Street Bathhouse and Keyes Memorial Beach | B. Lavatory | E. Exposed plumbing underneath | Women's Toilet Room | 1 |  | Priority 1 | Safety | Insulate or otherwise configure pipes to prevent contact for at least one lavatory. | 1 | 92
23 | Sea Street Bathhouse and Keyes Memorial Beach | B. Lavatory | E. Exposed plumbing underneath | Men’s Toilet Room | 1 |  | Priority 1 | Safety | Insulate or otherwise configure pipes to prevent contact for at least one lavatory. | 1 | 92
24 | Sea Street Bathhouse and Keyes Memorial Beach | D. Toilet Compartment | N. Non-compliant toilet paper dispenser | Women's Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate toilet paper so that it is located under the grab bar and higher than 15" above the finished floor; and between 7" and 9" from the front of the toilet. Or replace dispenser if it does not allow continuous paper flow. | 1 | 256
25 | Sea Street Bathhouse and Keyes Memorial Beach | D. Toilet Compartment | N. Non-compliant toilet paper dispenser | Men’s Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate toilet paper so that it is located under the grab bar and higher than 15" above the finished floor; and between 7" and 9" from the front of the toilet. Or replace dispenser if it does not allow continuous paper flow. | 1 | 256
26 | Sea Street Bathhouse and Keyes Memorial Beach | D. Toilet Compartment | R. Coat hook > 48" | Men’s Toilet Room | 1 |  | Priority 3 | Additional Access | Lower coat hook so that it is no higher than 48". | 1 | 150
27 | Sea Street Bathhouse and Keyes Memorial Beach | D. Toilet Compartment | R. Coat hook > 48" | Women's Toilet Room | 1 |  | Priority 3 | Additional Access | Lower coat hook so that it is no higher than 48". | 1 | 150
28 | Sea Street Bathhouse and Keyes Memorial Beach | F. Dispensers | E. Dispenser acts as a protruding object | Men’s Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate dispenser so it does not protrude into the circulation path. | 1 | 0
29 | Sea Street Bathhouse and Keyes Memorial Beach | F. Dispensers | E. Dispenser acts as a protruding object | Women's Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate dispenser so it does not protrude into the circulation path. | 1 | 0
30 | Sea Street Bathhouse and Keyes Memorial Beach | H. Outdoor Rinsing Showers | A. Rinsing shower not on an accessible route | Path to Outdoor Shower | Ext. |  | Priority 1 | Program Access | Provide an accessible route to the rinsing shower or locate a new rinsing shower on an accessible route. | 1 | 0
31 | Sea Street Bathhouse and Keyes Memorial Beach | H. Outdoor Rinsing Showers | B. Clear floor space not provided at rinsing shower D. 2 fixed shower heads not provided | Outdoor Shower | Ext. |  | Priority 1 | Program Access | Ensure there is a 60" by 60" clear floor space around outdoor rinsing shower. | 1 | 3119
32 | Sea Street Bathhouse and Keyes Memorial Beach | J. Portable Toilet | B. Accessible portable toilets not provided | By Parking Lot | Ext. |  | Priority 1 | Program Access | Provide an accessible portable toilet. | 1 | 0
33 | Sea Street Bathhouse and Keyes Memorial Beach | K. Changing Room | E. Room is < 78" x 72" | Men’s Changing Room | 1 |  | Priority 1 | Program Access | Provide an accessible changing room that is 78" by 72" minimum. | 1 | 5866
34 | Sea Street Bathhouse and Keyes Memorial Beach | K. Changing Room | E. Room is < 78" x 72" | Women's Changing Room | 1 |  | Priority 1 | Program Access | Provide an accessible changing room that is 78" by 72" minimum. | 1 | 5866
35 | Sea Street Bathhouse and Keyes Memorial Beach | C. Benches |  | Stair Beach Access 1 | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a 36" by 48" clear floor space adjacent to the bench. | 1 | 0
36 | Sea Street Bathhouse and Keyes Memorial Beach | C. Benches |  | Stair Beach Access 2 | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a 36" by 48" clear floor space adjacent to the bench. | 1 | 0
37 | Sea Street Bathhouse and Keyes Memorial Beach | C. Benches |  | Viewing Area | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing some benches with backs and some with arms. | 1 | 0
38 | Sea Street Bathhouse and Keyes Memorial Beach | C. Directional Signage |  | Path From Bathhouse to Stair Beach Access 1 | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a directional sign to the accessible route. Locate sign at the beginning of the route to minimize backtracking. | 1 | 0
39 | Sea Street Bathhouse and Keyes Memorial Beach | C. Directional Signage |  | Path From Beach Access 1 to Beach Access Stairs 2 | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a directional sign to the accessible route. Locate sign at the beginning of the route to minimize backtracking. | 1 | 0
40 | Sea Street Bathhouse and Keyes Memorial Beach | C. Directional Signage |  | Ramp -Employee's Office Side | Ext. |  | Priority 4 | Enhanced Usability | Recommend changing the sign with a sign that reads "Accessible Toilet Rooms". | 1 | 0
41 | Sea Street Bathhouse and Keyes Memorial Beach | C. Signage |  | Parking Lot | Ext. |  | Priority 4 | Enhanced Usability | Recommend providing a sign that reads "No Parking Any Time" to maintain clear space at the accessible route to the bathhouse and other amenities in the area. | 1 | 0
42 | Sea Street Bathhouse and Keyes Memorial Beach | C. Stairs |  | Staircase by Parking Lot |  |  | Priority 4 | Enhanced Usability | Recommend providing closed risers at the stairs. | 1 | 0

## US Customs Old Jail House
Town of Barnstable: Priority for ADA Transition Plan - Secondary Assets
**IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Barnstable
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | U.S. Custom House Old Jail | C. Off-Street Parking Lot or Garage | A. Total # of parking B. Total # of designated accessible parking spaces | Parking Lot | Ext. |  | Priority 1 | Program Access | Provide a van accessible parking space near the ramp that is 96" wide min. with a marked access aisle 96" wide min. Include an accessible parking identification sign. Add the designation "Van Accessible" to the sign. (Cost for a stone dust accessible parking space and path to ramp. See illustration in narrative report. Some additional material costs may be required.) | 1 | 1850
2 | U.S. Custom House Old Jail | G. Entrance | B. Entrance not on an accessible route C. Directional sign to accessible entrance not provided | Main Entrance to the Jail | Ext. |  | Priority 1 | Program Access | Provide a directional sign indicating the location of the nearest accessible entrance. | 1 | 346
3 | U.S. Custom House Old Jail | B. Interior Access Route | J. Running slope > 1:20 (5%) | Cells Area | 1 |  | Priority 3 | Additional Access | Staff should be available to assist wheelchair users up and down the ramp for safety purposes. | 1 | 0
4 | U.S. Custom House Old Jail | E. Exterior Ramp | H. Handrails have non-compliant cross section N. Landing has a slope > 1:50 in either direction Q. Edge protection < 4" high | Accessible Entrance/ Egress | Ext. |  | Priority 3 | Additional Access | Provide handrails with 1-1/4"to 1-1/2" circular cross sections. Alter so that the slope in all directions is no greater than 1:50 (2.00%). Provide edge protection that prevents the passage of a 4" diameter sphere, where any portion of the sphere is within 4" of the finished floor or ground surface. (Cost based on 4 sets of 20 foot long handrails and edge protection on wide side.) | 1 | 3520
5 | U.S. Custom House Old Jail | A. Exterior Access Route | N. Accessible route not provided | Accessible Entrance/ Egress | Ext. |  | Priority 1 | Program Access | Ensure an accessible route is provided to the ramp. (Cost provided in ID #1.) | 1 | 0

## Wequaquet Lake Beach & Bathhous
Town of Barnstable: Priority for ADA Transition Plan - Secondary Assets
**IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Barnstable
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | Wequaquet Lake Beach and Bathhouse | A. Exterior Access Route | E. Route obstructed by protruding objects | Towards Men's Toilet Room | Ext. |  | Priority 3 | Additional Access | Relocate concrete block to maintain the accessible route to the men's toilet room. | 1 | 0
2 | Wequaquet Lake Beach and Bathhouse | A. Exterior Access Route | F. Surface openings > 1/2" | Route to Bath House | Ext. |  | Priority 3 | Additional Access | Repair surface. Cost for a 4'x4' concrete patch. | 1 | 256
3 | Wequaquet Lake Beach and Bathhouse | A. Exterior Access Route | H. Running slope > 1:20 (5%) | Route From Parking Lot to Lake | Ext. |  | Priority 3 | Additional Access | Reduce running slope to be no steeper than 1:20 (5%). | 1 | 0
4 | Wequaquet Lake Beach and Bathhouse | A. Exterior Access Route | J. Level changes > 1/4" | Lake Front | Ext. |  | Priority 3 | Additional Access | Alter change in level to provide a 1:12 (8.33%) max. slope that connects to a beach mat. See ID #5 for mat cost. | 1 | 0
5 | Wequaquet Lake Beach and Bathhouse | C. Beach Access Routes | A. Beach route not provided | Lake Front | Ext. |  | Priority 1 | Program Access | Provide an accessible route that is firm and stable. Ensure the accessible route extends to the recreation water level . (Cost for a beach mat that is 5 ft wide and 30 ft.) | 1 | 1379
6 | Wequaquet Lake Beach and Bathhouse | E. Off-Street Parking Lot or Garage | M. Running or cross slope at access aisle > 1:50 (2.00%) | Parking Lot | Ext. |  | Priority 1 | Program Access | Reduce running or cross slope to be no steeper than 1:50 (2.00%). | 1 | 1440
7 | Wequaquet Lake Beach and Bathhouse | E. Off-Street Parking Lot or Garage | O. Sign does not have the designation "Van Accessible" | Parking Lot | Ext. |  | Priority 1 | Program Access | Add the designation "Van Accessible" to the sign located at the van accessible space. | 1 | 500
8 | Wequaquet Lake Beach and Bathhouse | G. Entrance | N. Threshold not beveled O. Threshold is > 1/2" high | Women's Toilet Room | Ext. |  | Priority 3 | Additional Access | Bevel threshold. Alter threshold to be 1/2" high max. | 1 | 300
9 | Wequaquet Lake Beach and Bathhouse | G. Entrance | N. Threshold not beveled O. Threshold is > 1/2" high | Women's Toilet Room | Ext. |  | Priority 3 | Additional Access | See ID #8. | 1 | 0
10 | Wequaquet Lake Beach and Bathhouse | G. Entrance | N. Threshold not beveled O. Threshold is > 1/2" high | Men's Toilet Room | Ext. |  | Priority 3 | Additional Access | Bevel threshold. Alter threshold to be 1/2" high max. | 1 | 300
11 | Wequaquet Lake Beach and Bathhouse | G. Entrance | N. Threshold not beveled O. Threshold is > 1/2" high | Men's Toilet Room | Ext. |  | Priority 3 | Additional Access | See ID #10. | 1 | 0
12 | Wequaquet Lake Beach and Bathhouse | C. Ramps | C. Running slope >1:12 (8.33%) | Route From Parking Lot to Lake | Ext. |  | Priority 3 | Additional Access | Reduce running slope to be no steeper than 1:12 (8.33%). | 1 | 0
13 | Wequaquet Lake Beach and Bathhouse | C. Ramps | J. Handrails have non-compliant cross section R. Edge protection < 4" high | Route From Parking Lot to Lake | Ext. |  | Priority 3 | Additional Access | Provide handrails with 1-1/4" to 1-1/2" circular cross section. Provide edge protection that prevents the passage of a 4" diameter sphere, where any portion of the sphere is within 4" of the finished floor surface. (Recommendation applies to all the ramp runs.) | 1 | 0
14 | Wequaquet Lake Beach and Bathhouse | C. Ramps | M. Landing < 60" min. long | Route From Parking Lot to Lake | Ext. |  | Priority 3 | Additional Access | Alter so the landing is 60" long min. | 1 | 0
15 | Wequaquet Lake Beach and Bathhouse | C. Ramps | M. Landing < 60" min. long | Route From Parking Lot to Lake | Ext. |  | Priority 3 | Additional Access | Alter so the landing is 60" long min. | 1 | 0
16 | Wequaquet Lake Beach and Bathhouse | C. Ramps | M. Landing < 60" min. long | Route From Parking Lot to Lake | Ext. |  | Priority 3 | Additional Access | Alter so the landing is 60" long min. | 1 | 0
17 | Wequaquet Lake Beach and Bathhouse | C. Ramps | V. Handrails not provided | Route From Parking Lot to Lake | Ext. |  | Priority 1 | Program Access | Provide handrails with 1-1/4" to 1-1/2" circular cross section. | 2 | 2640
18 | Wequaquet Lake Beach and Bathhouse | D. Stairways | C. Handrails do not extend 12" from stairs | Route From Parking Lot to Lake | Ext. |  | Priority 3 | Additional Access | Top: Ensure handrails extend horizontally above the landing for 12” min. beginning above the first riser nosing. Bottom: Ensure that the sloped bottom extension extends one tread depth minimum beyond last riser nosing in same direction as stair flight. | 2 | 400
19 | Wequaquet Lake Beach and Bathhouse | E. Signage | B. Raised characters not provided D. Braille not provided | Women's Toilet Room | Ext. |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille. | 1 | 232
20 | Wequaquet Lake Beach and Bathhouse | E. Signage | B. Raised characters not provided D. Braille not provided | Men's Toilet Room | Ext. |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille. | 1 | 232
21 | Wequaquet Lake Beach and Bathhouse | J. Picnic Tables | G. Toe or knee clearance at table not provided | Bath House Picnic Table | Ext. |  | Priority 1 | Program Access | Provide a picnic table with top between 28"- 34" above the ground and 27" clear height underneath. | 1 | 1400
22 | Wequaquet Lake Beach and Bathhouse | J. Picnic Tables | G. Toe or knee clearance at table not provided H. Picnic table not on an accessible route | Lake Front | Ext. |  | Priority 1 | Program Access | Provide at least one picnic table with top between 28"- 34" above the ground and 27" clear height underneath in this area. Ensure picnic table is on an accessible route. | 1 | 1400
23 | Wequaquet Lake Beach and Bathhouse | A. Overall Access | H. Audible and visible alarms not provided | Women's Toilet Room | 1 |  | Priority 3 | Additional Access | When fire system is updated, ensure that a visible and audible fire alarm is installed. | 1 | 0
24 | Wequaquet Lake Beach and Bathhouse | A. Overall Access | H. Audible and visible alarms not provided | Men's Toilet Room | 1 |  | Priority 3 | Additional Access | When fire system is updated, ensure that a visible and audible fire alarm is installed. | 1 | 0
25 | Wequaquet Lake Beach and Bathhouse | B. Lavatory | E. Exposed plumbing underneath | Women's Toilet Room | 1 |  | Priority 1 | Safety | Insulate or otherwise configure pipes to prevent contact for at least one lavatory. | 1 | 92
25 | Wequaquet Lake Beach and Bathhouse | B. Lavatory | F. Mirror above lavatory w/reflective surface > 40" | Women's Toilet Room | 1 |  | Priority 3 | Additional Access | Lower mirror so that the bottom surface is at 40" max. above the finished floor. | 1 | 256
26 | Wequaquet Lake Beach and Bathhouse | B. Lavatory | E. Exposed plumbing underneath | Men's Toilet Room | 1 |  | Priority 1 | Safety | Insulate or otherwise configure pipes to prevent contact for at least one lavatory. | 1 | 92
26 | Wequaquet Lake Beach and Bathhouse | B. Lavatory | F. Mirror above lavatory w/reflective surface > 40" | Men's Toilet Room | 1 |  | Priority 3 | Additional Access | Lower mirror so that the bottom surface is at 40" max. above the finished floor. | 1 | 256
27 | Wequaquet Lake Beach and Bathhouse | D. Toilet Compartment | D. Door with malfunctioning self-closing hinge R. Coat hook > 48" V. Door pull not provided | Women's Toilet Room | 1 |  | Priority 3 | Additional Access | Repair hinge. Lower coat hook so that it is no higher than 48". Provide a door pull on both sides of the door near the latch. | 1 | 220
28 | Wequaquet Lake Beach and Bathhouse | D. Toilet Compartment | N. Non-compliant toilet paper dispenser | Women's Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate toilet paper so that it is located under the grab bar and higher than 15" above the finished floor; and between 7" and 9" from the front of the toilet. | 1 | 256
29 | Wequaquet Lake Beach and Bathhouse | D. Toilet Compartment | N. Non-compliant toilet paper dispenser | Men's Toilet Room | 1 |  | Priority 3 | Additional Access | Relocate toilet paper so that it is located under the grab bar and higher than 15" above the finished floor; and between 7" and 9" from the front of the toilet. | 1 | 256
30 | Wequaquet Lake Beach and Bathhouse | D. Toilet Compartment | R. Coat hook > 48" | Men's Toilet Room | 1 |  | Priority 3 | Additional Access | Lower coat hook so that it is no higher than 48". | 1 | 150
31 | Wequaquet Lake Beach and Bathhouse | E. Urinal | D. Urinal recessed > 24" has > 36" clear width | Men's Toilet Room | 1 |  | Priority 3 | Additional Access | If urinal is recessed greater than 24" ensure there is a clear width of 36". Recommend relocating the partition. | 1 | 256
32 | Wequaquet Lake Beach and Bathhouse | J. Portable Toilet | B. Accessible portable toilets not provided | Near Men's Toilet Room | Ext. |  | Priority 1 | Program Access | Ensure that at least 5% of portable toilets are accessible. |  | 0

## West Barnstable Train Station
Town of Barnstable: Priority for ADA Transition Plan - Secondary Assets
**IHCD Cost Estimation Notes: - Cost of design is not included. - Does not include costs when note indicates future work. - Labor cannot be estimated for all remedies. - There is no cost noted when it's presumed to be a maintenance issue. - Cost based on a national average. Cost is not based on prevailing wage. Estimates are intended as a guide to budgeting access modifications and are not intended to be absolutely comprehensive or definitive.
| Priorities: Priority 1: Program Access* or Safety Priority 2: Navigational Issue Priority 3: Additional Access* Priority 4: Enhanced Usability | [5 empty] | *Note: Some toilet rooms issues compromise Program Access. Some toilet rooms with less central issues (e.g., partially accessible toilet rooms), fall under Additional Access.
| Information Provided by Institute for Human Centered Design | [10 empty] | Project Management for the Town of Barnstable
ID | Facility Name | Element | Issue/Physical Barrier | Location | Fl. | Rm. | Town Priority | Priority for Barrier Removal | Remedies | Quantity | Estimated Cost of Barrier Removal | Project Start Date | Project Completion Date | Responsible for Barrier Removal
1 | West Barnstable Train Station | A. Exterior Access Route | F. Surface openings > 1/2" | Platform - West | Ext. |  | Priority 3 | Additional Access | Repair surface. | 1 | 0
2 | West Barnstable Train Station | A. Exterior Access Route | F. Surface openings > 1/2" | Platform - North - East | Ext. |  | Priority 3 | Additional Access | Repair surface. | 1 | 0
3 | West Barnstable Train Station | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Entrance/ Exit - East Side | Ext. |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
4 | West Barnstable Train Station | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | Platform - North Side | Ext. |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
5 | West Barnstable Train Station | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) | North East Near Accessible Parking | Ext. |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). | 1 | 0
6 | West Barnstable Train Station | A. Exterior Access Route | G. Cross slope > 1:50 (2.00%) H. Running slope > 1:20 (5%) | Near Display - West Side | Ext. |  | Priority 3 | Additional Access | Reduce cross slope to be no steeper than 1:50 (2.00%). Reduce running slope to be no steeper than 1:20 (5%). | 1 | 0
7 | West Barnstable Train Station | A. Exterior Access Route | H. Running slope > 1:20 (5%) | To Platform & Ramp | Ext. |  | Priority 3 | Additional Access | Reduce running slope to be no steeper than 1:20 (5%). | 1 | 0
8 | West Barnstable Train Station | A. Exterior Access Route | J. Level changes > 1/4" | Ramp Top to Raised Platform - West | Ext. |  | Priority 3 | Additional Access | Alter change in level to be 1/4" high max. | 1 | 0
9 | West Barnstable Train Station | A. Exterior Access Route | J. Level changes > 1/4" | To Ramp From North Side | Ext. |  | Priority 3 | Additional Access | Alter change in level to be 1/4" high max. | 1 | 0
10 | West Barnstable Train Station | A. Exterior Access Route | K. Surface is not stable, firm, and slip-resistant | South Side | Ext. |  | Priority 3 | Additional Access | Repair surface. | 1 | 0
11 | West Barnstable Train Station | A. Exterior Access Route | K. Surface is not stable, firm, and slip-resistant | Toward Ramp - West Side | Ext. |  | Priority 3 | Additional Access | Repair surface. | 1 | 0
12 | West Barnstable Train Station | A. Exterior Access Route | K. Surface is not stable, firm, and slip-resistant | North East Side Near Accessible Parking | Ext. |  | Priority 3 | Additional Access | Repair surface. | 1 | 0
13 | West Barnstable Train Station | C. Off-Street Parking Lot or Garage | O. Sign does not have the designation "Van Accessible" | Accessible Parking - East Side | Ext. |  | Priority 1 | Program Access | Provide a marked access aisle that is at least 96" wide. Add the designation "Van Accessible" to the sign located at the van accessible space. | 1 | 500
14 | West Barnstable Train Station | E. Exterior Ramp | L. Landing < 60" min. long |  | Ext. |  | Priority 3 | Additional Access | Alter so the landing is 60" long min. | 1 | 0
15 | West Barnstable Train Station | G. Entrance | C. Directional sign to accessible entrance not provided | Main Entrance/Exit | Ext. |  | Priority 1 | Program Access | Provide a directional sign indicating the location of the nearest accessible entrance. | 1 | 346
16 | West Barnstable Train Station | G. Entrance | C. Directional sign to accessible entrance not provided | Entrance/ Exit - East Side | Ext. |  | Priority 1 | Program Access | Provide a directional sign indicating the location of the nearest accessible entrance. | 1 | 346
17 | West Barnstable Train Station | G. Entrance | D. International Symbol of Accessibility not provided Q. Hardware not operable with a closed fist | Entrance/ Exit - North East | Ext. |  | Priority 1 | Program Access | Provide a sign with the International Symbol of Accessibility (ISA). Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. Cost to provide compliant hardware is not included. | 1 | 232
18 | West Barnstable Train Station | G. Entrance | D. International Symbol of Accessibility not provided Q. Hardware not operable with a closed fist | Middle Entrance/ Exit - North Side | Ext. |  | Priority 1 | Program Access | Provide a sign with the International Symbol of Accessibility (ISA). Provide hardware that can be operable with one hand and not require tight grasping, pinching, or twisting of the wrist. Cost to provide compliant hardware is not included. | 1 | 232
19 | West Barnstable Train Station | G. Entrance | K. Maneuvering clearance at door > 1:50 (2.00%) | Entrance/ Exit - Baggage Room (North) | Ext. |  | Priority 3 | Additional Access | Alter so that the slope in all directions is no greater than 1:50 (2.00%). After the slope is made compliant, provide a sign with the International Symbol of Accessibility (ISA). | 1 | 0
20 | West Barnstable Train Station | G. Entrance | K. Maneuvering clearance at door > 1:50 (2.00%) | Entrance/ Exit - Baggage Room (South) | Ext. |  | Priority 3 | Additional Access | Alter so that the slope in all directions is no greater than 1:50 (2.00%). After the slope is made compliant, provide a sign with the International Symbol of Accessibility (ISA). | 1 | 0
21 | West Barnstable Train Station | G. Entrance | N. Threshold not beveled O. Threshold > 1/2" high | Entrance/ Exit - North East | Ext. |  | Priority 3 | Additional Access | Bevel the threshold. Alter threshold to be 1/2" high max. | 1 | 0
22 | West Barnstable Train Station | A. Means of Egress | B. Tactile exit sign not provided | Entrance/ Exit - Baggage Room (South) | 1 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. If an illuminated exit sign is provided, ensure the sign has the International Symbol of Accessibility (ISA). | 1 | 232
23 | West Barnstable Train Station | A. Means of Egress | B. Tactile exit sign not provided | Middle Entrance/ Exit - North | 1 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. If an illuminated exit sign is provided, ensure the sign has the International Symbol of Accessibility (ISA). | 1 | 232
24 | West Barnstable Train Station | A. Means of Egress | B. Tactile exit sign not provided | Entrance/ Exit - North, Baggage Room | 1 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. If an illuminated exit sign is provided, ensure the sign has the International Symbol of Accessibility (ISA). | 1 | 232
25 | West Barnstable Train Station | A. Means of Egress | B. Tactile exit sign not provided | To North East Exit | 1 |  | Priority 1 | Safety | Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. If an illuminated exit sign is provided, ensure the sign has the International Symbol of Accessibility (ISA). | 1 | 232
26 | West Barnstable Train Station | A. Means of Egress | B. Tactile exit sign not provided C. Directional sign to accessible emergency exit not provided | Main Entrance/Exit | 1 |  | Priority 1 | Safety | Provide a directional sign indicating the location of the nearest accessible emergency exit. Ensure tactile exit sign with raised characters and braille is provided at exit door. Mount sign between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 432
27 | West Barnstable Train Station | A. Means of Egress | B. Tactile exit sign not provided C. Directional sign to accessible emergency exit not provided | To Entrance/ Exit Near Men's Toilet Room | 1 |  | Priority 1 | Safety | Provide a directional sign indicating the location of the nearest accessible emergency exit. Ensure tactile exit signs with raised characters and braille are provided at exit doors. Mount signs between 48”- 60” above the finished floor located on the latch side of the door. | 1 | 432
28 | West Barnstable Train Station | B. Interior Access Route | A. Route < 36" wide | Baggage Room | 1 |  | Priority 3 | Additional Access | Ensure that a clear width of 36" min. is maintained at the accessible route. | 1 | 0
29 | West Barnstable Train Station | B. Interior Access Route | B. Obstructed by protruding objects | Ticket Counter - Main Lobby | 1 |  | Priority 3 | Additional Access | Provide a cane-detectable barrier. | 2 | 512
30 | West Barnstable Train Station | H. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Men's Toilet Room | 1 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on sign. Locate sign alongside the door on the latch side. | 1 | 232
31 | West Barnstable Train Station | H. Signage | B. Raised characters not provided on sign D. Braille not provided on sign G. Sign not located on the latch side of the door | Women's Toilet Room | 1 |  | Priority 2 | Navigational Issue | Provide text with raised characters duplicated in braille on sign. Locate a sign on the latch side. | 1 | 232
32 | West Barnstable Train Station | M. Dining or Work Surfaces | C. Knee or toe clearance not provided | Baggage Room | 1 |  | Priority 1 | Program Access | Provide a work surface with 27" min. knee and toe clearance. | 1 | 700
33 | West Barnstable Train Station | N. Assembly Area | P. Assistive listening devices not provided | Main Lobby | 1 |  | Priority 1 | Program Access | If audible communication is integral to the use of the space, provide an assistive listening system. | 1 | 0
34 | West Barnstable Train Station | A. Overall Access | C. Accessible plumbing fixtures or stalls not provided | Men's Toilet Room | 1 |  | Priority 1 | Program Access | If the toilet is open to members of the public, ensure an accessible toilet room is provided. | 1 | 0
35 | West Barnstable Train Station | A. Overall Access | C. Accessible plumbing fixtures or stalls not provided | Women's Toilet Room | 1 |  | Priority 1 | Program Access | If the toilet is open to members of the public, ensure an accessible toilet room is provided. | 1 | 0
36 | West Barnstable Train Station | A. Display |  | Near Men's Toilet Room | 1 |  | Priority 4 | Enhanced Usability | Recommend relocating display to avoid glare. | 1 | 0
37 | West Barnstable Train Station | A. Display |  | Near Entrance/ Exit - North East | 1 |  | Priority 4 | Enhanced Usability | Recommend relocating display to avoid glare and provide clear visibility to the display in the back. | 1 | 0
38 | West Barnstable Train Station | A. Signage |  | Near Women's Toilet Room | 1 |  | Priority 4 | Enhanced Usability | Recommend relocating the sign to prevent glare. | 1 | 0
39 | West Barnstable Train Station | C. Signage |  | Entrance/Exit Near Men's Toilet Room | 1 |  | Priority 4 | Enhanced Usability | Recommend locating the sign at least 48" above the finished floor. See ID #27. | 1 | 0